Deans Community High School

School Improvement Plan

2026-2027

Head Teacher’s Introduction

The Head Teacher is supported by a leadership team of 3 Depute Head Teachers and 11 Principal Teachers. The school’s vision was co-created, leading to a clear statement on what our school community is striving towards and which areas should therefore be the focus of our improvement. The vision and values of our school underpin the work that takes place within the classroom and beyond, and the strong positive relationships between students and staff are evident throughout the school. All members of the school community and partners are involved in evaluating the impact of the work of the school.

Our Shared Vision

Students at Deans Community High School will be inspired through high quality learning and teaching, in a safe, inclusive environment, to confidently achieve and attain the very best they can to succeed in life, learning and work.

Our Shared Values

INCLUSION		RESPECT		INTEGRITY		COMPASSION		ASPIRATION

Our School Aims

ATTAINMENT AND ACHIEVEMENT

To raise standards of educational attainment for all in school, especially in the core skills of literacy and numeracy, and to achieve better levels in national measures of achievement including examination results.

FRAMEWORK FOR LEARNING

To support and develop the skills of teachers, the self-discipline of pupils and to enhance school environments so that they are conducive to teaching and learning.

INCLUSION AND EQUALITY

To promote equality and help every pupil benefit from education, with particular regard paid to pupils with additional support needs, and to other lesser used languages.

VALUES AND CITIZENSHIP

To work with parents to teach pupils respect for self and one another and their interdependence with other members of their neighbourhood and society, and to teach them the duties and responsibilities of citizenship in a democratic society.

Our self-evaluation, particularly within learning and teaching, well being and school ethos, has given us a clear indication of the areas to prioritise for this session’s improvements, all of which are detailed in this plan and have been shared and agreed with staff, students and parents/carers.

Raising Educational Attainment Strategy 2023-2028

Outcome 1 – Learning and Curriculum

Ensuring every child and young person experiences varied, vibrant and challenging learning experiences which are built on the provision of high quality and inclusive learning, teaching and assessment. Fundamental to this is the design and implementation of a curriculum that creates the conditions, culture and ethos for all four capacities (successful learners, confident individuals, responsible citizens and effective contributors) to thrive and be equally valued.

Outcome 2 – Wellbeing, Inclusion and Attendance

Improving wellbeing, inclusion and attendance for all children and young people, promoting confidence, independent thinking and resilience. Fundamental to this is working with families and partners to support the highest possible levels of engagement and equity for all. Improving health and wellbeing for all children and young people will lead to raised educational attainment and achievement, ensuring that learning promotes confidence, resilience, engagement, independent thinking and positive mindsets which in turn increase personal, social, cultural and economic opportunities.

National Improvement Framework

NIF sketchnote 2025

West Lothian Raising Education Attainment Strategy 2023-2028

Summary of Priorities 2026-2027

Improve:

- Use of targeted interventions to improve overall attendance

- Approaches to planning, tracking and monitoring of assessment

- To improve learner’s outcomes in L5 and L6 attainment

Understand:

- How will the new developments of the curriculum improvement cycles impact on our school?

- To develop a shared understanding of what inclusive curriculum involves

Consolidate:

- Positive destinations remaining above 94%

- Meeting the needs of all learners and engaging in professional learning to support this

- The embedding of the schools Positive Relationships policy

Priorities for Improvement

Raising Attainment and Achievement

| Desired Outcome | Aims (STAN*) | QIs | Action(s) | Timeline | Who | What do we need to know? How will we measure it? | Progress Update |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Improvement in QS attainment levels and quality of pass. | By August 2027, attainment within S4 of 5 or more at level 5 SQA improves to a minimum of 38% | 1.1 1.3 1.4 2.2 2.3 2.4 3.2 | Analysis of Aug ’26 SQA results and tracking data from session 25/26 to highlight trend and anomalies. | Sep ‘26 | HT DHT’s | 5-year trend identified Comparison with VC Comparisons with predictions from tracking data Comparisons from SLT attainment meetings Comparison of Estimate data |  |
|  | By August 2027, attainment within S5 of 5 or more at level 6 SQA improves to a minimum of 16% |  | Students’ subjects and presentation levels analysed and risk assessed. Appropriate mitigations taken throughout the session. Particular focus at key points post assessment and prior to QS exam diet. | Aug ’26 – May ‘27 | HT DHT’s SLT | Risk assessed data discussed within SLT Ongoing tracking data shows identified targets being met at N5/H/AH level |  |
|  | By August 2027, attainment within S5 of 3 or more at level 6 SQA improves to minimum of 38% |  | All S5 students interviewed upon return in August and recourse if necessary to maximise chances of progression based on N5 results. | Aug - Sep ‘26 | DHT’s | Risk assessed data discussed within SLT at fortnightly meetings. Non-negotiables shared with teachers. Ongoing tracking of attainment of each student shows targets are being met. Interventions discussed at SLT and individual attainment meetings |  |
|  | By August 2027, attainment within S5 of 1 or more at level 6 SQA improves to minimum of 52% |  | Analysis of Aug 2026 results to identify strengths and areas for improvement. | Aug – Sep ‘26 | SMT PTC/PT’s |  |  |
|  | By August 2027, attainment within S6 of 1 or more at level 7 SQA improves to minimum of 15% |  |  |  |  |  |  |
|  | By Aug 2027 N5 and H A-band pass rates will have increased by 2 % |  | Reflection in DIP/ FIP’s. Component mark analysis Power Bi comparison across WL schools Targets set at attainment meetings | Aug ’26 – May ‘27 | SMT PTC/PT’s | Data gathered through Power Bi and Insight Ongoing tracking of attainment of each student shows targets are being met. Interventions discussed at SLT and individual attainment meetings |  |

* Specific, Timebound, Aligned and Numeric

Approaches to Planning, Tracking & Assessment

| Desired Outcome | Aims (STAN*) | QIs | Action(s) | Timeline | Who | What do we need to know? How will we measure it? | Progress Update |
| --- | --- | --- | --- | --- | --- | --- | --- |
| We have effective Planning, Tracking, Monitoring & Assessment approaches in the BGE and SP | By Oct ’26 we will have a newly developed tracking and monitoring system in place for the BGE | 1.1 1.3 1.4 2.6 3.2 | BGE Tracking and monitoring system developed. | Aug-Oct ’26 | DHT/PTC working group | Audit of current systems |  |
|  | By Dec ’26 all staff will understand the purpose of T&M and assessment in the BGE and their role within it. |  | Assessment approaches explored and embedded into the curriculum. Teaching staff confident in AIFL – Summative and Formative approaches to assessment. | Aug ’26 – May ‘27 | SMT SLT | Review levels of confidence from VSE and 25/26 school level observations Confidence levels from L&T in school afternoons 26/27 L&T observations |  |
|  | By Dec ’26 newly developed assessment and moderation procedures will be in place for all departments |  | Ensure adaptations are underpinned and aligned with effective moderation. | Aug ’26 – May ‘27 | SMT SLT | Analysis of adaptations Analysis of learner voice |  |
|  | By May ’27 reporting systems will be updated | 1.1 | Parent/Pupil/Staff consultation on reporting systems of tracking and monitoring of pupil progress. Plan developed for improvement of systems and consulted on by whole school community. | Aug ’26 – May ‘27 | DHT’s | Information from consultations of current systems of reporting on pupil progress. New reporting policy developed |  |

* Specific, Timebound, Aligned and Numeric

Wellbeing Equality & Inclusion - Attendance

| Desired Outcome | Aims (STAN*) | QIs | Action(s) | Timeline | Who | What do we need to know? How will we measure it? | Progress Update |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Improved use of targeted approaches to improve attendance | By June ‘27 overall attendance will rise by 1% to 85% | 1.1 2.4 2.7 3.1 | Students most at risk identified and tracked. | Sep ’26 – June ‘27 | DHT Support PTC’s Support | Data gathered through Power Bi Tracking systems used to measure progress of identified students Use WL Positive Relationships Policy to develop strategic Plan Audit effectiveness at key stages throughout the year Oct/Dec/Feb/April/June Monthly tracking of attendance targets at PTC DM’s |  |
|  | By June ’27 Q1 attendance will rise by 1% to 82% |  | Strategic attendance plan developed with clear roles, responsibilities and interventions. Work closely with authority lead for attendance to develop interventions | Sep ‘26 | DHT Support Full Pastoral Team |  |  |
|  | By June ’27 Free school meals attendance will rise by 1% to 74% |  | Family support worker caseload identified and tracked | Aug ’26 – June ‘27 | DHT Support Family support Worker |  |  |

* Specific, Timebound, Aligned and Numeric

Priorities for Consolidation

Meeting Learners needs – Positive Destinations

| Desired Outcome | Aims (STAN*) | QIs | Action(s) | Timeline | Who | What do we need to know? How will we measure it? | Progress Update |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Positive Destinations to remain above 94% | Overall destinations to increase to 95% | 2.6 2.7 3.1 3.3 | Students identified as being at risk of a negative destination by October ’26 Census date are identified | Aug ’26 | DHT Support PTC’s Support Collaborative Hub | Using data from Power Bi, SDS and leavers data to track. Weekly Collaborative hub Meetings for interventions and tracking |  |
|  | Q1 destinations to improve to 88% |  | interventions put in place for identified at risk pupils | Aug – Oct ‘26 | DHT Support PTC’s Support Collaborative Hub |  |  |
|  | FSM Positive Destinations increase to 90% |  | Weekly collaborative Hub Meetings |  | DHT Support PTC’s Support Collaborative Hub | Partnership working to be tracked for successful interventions |  |
|  | ASN Pupils increase to 88% |  |  |  |  |  |  |

* Specific, Timebound, Aligned and Numeric

Meeting Learners needs – Inclusive pedagogy

| Desired Outcome | Aims (STAN*) | QIs | Action(s) | Timeline | Who | What do we need to know? How will we measure it? | Progress Update |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To consolidate focus on Meeting Learner Needs through inclusive practice and pedagogy | By June ’27 SLT will have a shared understanding of what meeting the learner’s needs in the classroom looks like. | 1.2 1.3 2.3 | Shared effective practice from SMT and SLT will begin to build capacity within departments around pupil discourse and Learning Intentions and Success Criteria | Aug ’26 – Jun ‘27 | SMT SLT | Lesson Observations Learner Voice Learning Walks Record of engagement in CLPL Professional Dialogue |  |
|  | By Oct ’26 a 3-year strategic plan for moving from G to VG in 2.3 will be developed. |  | All teaching staff will challenge and build upon their classroom practice through engagement in the schools ‘moving from good to very good’ programme through a thinking classroom approach | Aug ’26 -Jun ‘27 | All teaching staff |  |  |

* Specific, Timebound, Aligned and Numeric

Wellbeing Equality & Inclusion – Positive Relationships Policy

| Desired Outcome | Aims (STAN*) | QIs | Action(s) | Timeline | Who | What do we need to know? How will we measure it? | Progress Update |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To embed the DCHS Positive Relationships Policy | By Dec ’26 all stakeholders are aware of the policy and its procedures | 1.1 3.1 | Students will be supported through assemblies, PSE and tutor to understand the policy and their role in its implementation. | Aug – Dec ‘26 | DHT Support PTC’s Support Tutor Teachers | Student Council Minutes Learner Voice Analysis of GIRFEC reporting |  |
|  |  |  | Policy is highlighted to parents via Parent Council, school newsletter and school website | Aug – Dec ‘26 | HT DHT Support | Parent Council Minutes Parental Survey Ethos Survey |  |
|  | By April ’27 a refresh of the school vision and values will be completed and relaunched |  | Review undertaken of current school vision statement and values by all stakeholders. | Aug – Oct ‘26 | HT DHT Support | Audit current views Learner Voice Parent feedback Staff Feedback |  |
|  |  |  | All stakeholders to be consulted on a refresh of vision and values. | Oct ‘26 – Dec ‘27 | HT DHT Support | Student Council Minutes Parent Council Minutes |  |
|  |  |  | Refresh of Vision and Values | Jan – April ‘27 | HT DHT Support | Learner Voice Observations |  |
|  | By May ’27 PSHE programme will be refreshed and reviewed in line with National Guidance |  | Review of PSHE programme in line with National Guidance | May ‘27 | HT DHT Support PTC’s Support | Audit current provision Learner Voice Student Council Minutes |  |

* Specific, Timebound, Aligned and Numeric

Priorities for Understanding

Meeting Learners Needs – Curriculum Improvement Cycle

| Desired Outcome | Aims (STAN*) | QIs | Action(s) | Timeline | Who | What do we need to know? How will we measure it? | Progress Update |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DCHS staff have increased awareness of the national CIC and opportunity to inform change where possible | By June 2027 almost all staff will understanding to the four contexts of learning in relation to the CIC in their subject areas | 2.2 2.3 | Ongoing support of staff in understanding the implications of changes to the national curriculum | Aug ’26 – June ‘27 | All teaching staff CIC Lead | Engagement in CIC activities throughout the session. DM Minutes |  |
| To develop a shared understanding of what inclusive curriculum and pedagogy involve | By January 2027, almost all staff will demonstrate a shared understanding of curriculum making. By June 2027 almost all staff will apply this understanding to the four contexts of learning in CfE | 2.2 2.3 | Participation by staff in authority led opportunities and activities organised by school strategic lead | Throughout the session as per calendar | All staff CIC secondary authority development postholders CIC school strategic leads | The CIC central strategic group will define measures | The CIC central strategic group will measure progress |

* Specific, Timebound, Aligned and Numeric